## Dashboard
SecureWatch Backlog Dashboard
Total User Stories | 33
Total Technical Tasks | 263
Completed Tasks | 0
In Progress Tasks | 0
Blocked Tasks | 0
Overall Progress | 0
Phase | User Stories | Technical Tasks | Done Tasks
Phase 1 | 4 | 34 | 0
Phase 2 | 3 | 23 | 0
Phase 3 | 7 | 52 | 0
Phase 4 | 4 | 31 | 0
Phase 5 | 6 | 49 | 0
Phase 6 | 3 | 24 | 0
Phase 7 | 6 | 50 | 0

## User Stories
HU ID | Title | User Story | Phase | Phase Name | MoSCoW | Priority | Status | Owner | Component | Story Points | Task Count | Progress
HU-00 | Project initialization | As a developer, I want to create the base project structure to organize all services, documentation, and configuration from the start. | Phase 1 | Project Foundation | Must Have | High | To Do | Developer | Repo base | 10 | 10 | 0
HU-01 | Define base architecture | As a developer, I want to document the system architecture to guide SecureWatch implementation. | Phase 1 | Project Foundation | Must Have | High | To Do | Developer | Architecture | 8 | 8 | 0
HU-02 | Configure local infrastructure | As a developer, I want to run the base infrastructure with Docker Compose to execute the system reproducibly. | Phase 1 | Project Foundation | Must Have | High | To Do | Developer | Infrastructure | 8 | 8 | 0
HU-03 | Create API Gateway | As a developer, I want to create an API Gateway to centralize frontend requests. | Phase 1 | Project Foundation | Must Have | High | To Do | Backend | API Gateway | 8 | 8 | 0
HU-04 | Register user | As a user, I want to register in the system so I can access SecureWatch. | Phase 2 | Security and Users | Must Have | High | To Do | Backend/Frontend | Auth | 8 | 8 | 0
HU-05 | Sign in | As a user, I want to sign in to access system functionality. | Phase 2 | Security and Users | Must Have | High | To Do | Backend/Frontend | Auth | 8 | 8 | 0
HU-06 | Manage roles | As an administrator, I want to assign roles to users to control access to functionality. | Phase 2 | Security and Users | Must Have | High | To Do | Backend/Frontend | Auth | 8 | 7 | 0
HU-07 | Create case | As an analyst, I want to create an analysis case to group digital evidence. | Phase 3 | Cases and Evidence | Must Have | High | To Do | Backend/Frontend | Cases | 8 | 8 | 0
HU-08 | List and filter cases | As an analyst, I want to browse existing cases to track their status. | Phase 3 | Cases and Evidence | Must Have | Medium | To Do | Backend/Frontend | Cases | 8 | 8 | 0
HU-09 | View case details | As an analyst, I want to view case details to review evidence, tasks, findings, and reports. | Phase 3 | Cases and Evidence | Must Have | High | To Do | Backend/Frontend | Cases | 8 | 8 | 0
HU-10 | Update case | As an analyst, I want to edit a case to correct information or change priority. | Phase 3 | Cases and Evidence | Should Have | Medium | To Do | Backend/Frontend | Cases | 5 | 7 | 0
HU-11 | Upload evidence | As an analyst, I want to upload digital evidence to a case so the system can analyze it. | Phase 3 | Cases and Evidence | Must Have | High | To Do | Backend/Frontend | Evidence | 13 | 8 | 0
HU-12 | Validate evidence | As the system, I want to validate uploaded files to avoid unsupported or unsafe content. | Phase 3 | Cases and Evidence | Must Have | High | To Do | Backend | Evidence | 8 | 7 | 0
HU-13 | Classify evidence | As the system, I want to classify evidence by type to decide which worker should process it. | Phase 3 | Cases and Evidence | Must Have | High | To Do | Backend | Evidence | 8 | 6 | 0
HU-14 | Create tasks automatically | As the system, I want to create processing tasks for each evidence item to distribute the work. | Phase 4 | Distributed Orchestration | Must Have | High | To Do | Backend | Tasks | 13 | 8 | 0
HU-15 | Queue tasks in RabbitMQ | As the system, I want to send tasks to message queues for asynchronous processing. | Phase 4 | Distributed Orchestration | Must Have | High | To Do | Backend | Messaging | 13 | 8 | 0
HU-16 | Process text | As the system, I want to analyze text evidence to detect keywords, categories, and risks. | Phase 5 | Workers | Must Have | High | To Do | Worker | Text Worker | 13 | 10 | 0
HU-17 | Process PDF documents | As the system, I want to extract text from documents and send it to text analysis. | Phase 5 | Workers | Must Have | High | To Do | Worker | Document Worker | 13 | 8 | 0
HU-18 | Process images | As the system, I want to analyze images to detect objects, labels, or risk elements. | Phase 5 | Workers | Should Have | Medium | To Do | Worker | Image Worker | 13 | 8 | 0
HU-19 | Process audio | As the system, I want to transcribe audio files so they can be analyzed as text. | Phase 5 | Workers | Should Have | Medium | To Do | Worker | Audio Worker | 13 | 8 | 0
HU-20 | Register findings | As the system, I want to register findings related to evidence and tasks to maintain traceability. | Phase 5 | Workers | Must Have | High | To Do | Backend/Worker | Findings | 8 | 8 | 0
HU-21 | Calculate case risk | As the system, I want to calculate a consolidated risk level to prioritize case review. | Phase 5 | Workers | Should Have | Medium | To Do | Backend | Risk | 8 | 7 | 0
HU-22 | Generate report | As an analyst, I want to generate a consolidated report to review analysis results. | Phase 6 | Results | Must Have | High | To Do | Backend | Reports | 13 | 10 | 0
HU-23 | Download and view report | As an analyst, I want to download or view the report to share case results. | Phase 6 | Results | Must Have | Medium | To Do | Backend/Frontend | Reports | 8 | 7 | 0
HU-24 | General dashboard | As a user, I want to see a dashboard to monitor cases, tasks, and workers. | Phase 7 | Monitoring and Presentation | Must Have | High | To Do | Backend/Frontend | Dashboard | 13 | 8 | 0
HU-25 | Real-time updates | As a user, I want automatic updates to know processing progress. | Phase 7 | Monitoring and Presentation | Should Have | Medium | To Do | Backend/Frontend | Realtime | 8 | 8 | 0
HU-26 | Internal alerts | As a user, I want to receive alerts when severe findings are detected. | Phase 6 | Results | Should Have | Medium | To Do | Backend/Frontend | Notifications | 8 | 7 | 0
HU-27 | Retries and dead-letter queue | As the system, I want to retry failed tasks and isolate tasks that cannot be completed. | Phase 4 | Distributed Orchestration | Must Have | High | To Do | Backend | Messaging | 8 | 8 | 0
HU-28 | Cancel task or case | As an analyst, I want to cancel a case or task to stop unnecessary processing. | Phase 4 | Distributed Orchestration | Should Have | Medium | To Do | Backend/Frontend | Tasks | 8 | 7 | 0
HU-29 | Audit trail | As a supervisor, I want to query important system actions to maintain traceability. | Phase 7 | Monitoring and Presentation | Should Have | Medium | To Do | Backend/Frontend | Audit | 8 | 8 | 0
HU-30 | Metrics and observability | As a developer, I want to expose system metrics to evaluate performance and scalability. | Phase 7 | Monitoring and Presentation | Must Have | High | To Do | DevOps | Observability | 8 | 8 | 0
HU-31 | Load testing | As a developer, I want to run load tests to demonstrate improvement with multiple workers. | Phase 7 | Monitoring and Presentation | Should Have | Medium | To Do | QA/DevOps | Load Testing | 8 | 8 | 0
HU-32 | Project documentation | As a developer, I want to document the project to simplify installation, evaluation, and usage. | Phase 7 | Monitoring and Presentation | Must Have | Medium | To Do | Documentation | Docs | 8 | 10 | 0

## Technical Tasks
HU ID | Task ID | Technical Task | Phase | Phase Name | Component | Priority | Status | Owner | Estimate | Start Date | Due Date | HU Title
HU-00 | HU-00-T01 | Create GitHub repository | Phase 1 | Project Foundation | Repo base | High | To Do | Developer |  |  |  | Project initialization
HU-00 | HU-00-T02 | Define open source license | Phase 1 | Project Foundation | Repo base | High | To Do | Developer |  |  |  | Project initialization
HU-00 | HU-00-T03 | Create initial README | Phase 1 | Project Foundation | Repo base | High | To Do | Developer |  |  |  | Project initialization
HU-00 | HU-00-T04 | Create monorepo structure | Phase 1 | Project Foundation | Repo base | High | To Do | Developer |  |  |  | Project initialization
HU-00 | HU-00-T05 | Create folders for frontend, backend, workers, infrastructure, and docs | Phase 1 | Project Foundation | Repo base | High | To Do | Developer |  |  |  | Project initialization
HU-00 | HU-00-T06 | Add .gitignore | Phase 1 | Project Foundation | Repo base | High | To Do | Developer |  |  |  | Project initialization
HU-00 | HU-00-T07 | Add .env.example | Phase 1 | Project Foundation | Repo base | High | To Do | Developer |  |  |  | Project initialization
HU-00 | HU-00-T08 | Add initial Docker Compose | Phase 1 | Project Foundation | Repo base | High | To Do | Developer |  |  |  | Project initialization
HU-00 | HU-00-T09 | Configure Conventional Commits | Phase 1 | Project Foundation | Repo base | High | To Do | Developer |  |  |  | Project initialization
HU-00 | HU-00-T10 | Create Kanban board | Phase 1 | Project Foundation | Repo base | High | To Do | Developer |  |  |  | Project initialization
HU-01 | HU-01-T01 | Define main services | Phase 1 | Project Foundation | Architecture | High | To Do | Developer |  |  |  | Define base architecture
HU-01 | HU-01-T02 | Design container diagram | Phase 1 | Project Foundation | Architecture | High | To Do | Developer |  |  |  | Define base architecture
HU-01 | HU-01-T03 | Design evidence upload flow | Phase 1 | Project Foundation | Architecture | High | To Do | Developer |  |  |  | Define base architecture
HU-01 | HU-01-T04 | Design RabbitMQ processing flow | Phase 1 | Project Foundation | Architecture | High | To Do | Developer |  |  |  | Define base architecture
HU-01 | HU-01-T05 | Design report generation flow | Phase 1 | Project Foundation | Architecture | High | To Do | Developer |  |  |  | Define base architecture
HU-01 | HU-01-T06 | Document technical decisions | Phase 1 | Project Foundation | Architecture | High | To Do | Developer |  |  |  | Define base architecture
HU-01 | HU-01-T07 | Define communication between services | Phase 1 | Project Foundation | Architecture | High | To Do | Developer |  |  |  | Define base architecture
HU-01 | HU-01-T08 | Define main system events | Phase 1 | Project Foundation | Architecture | High | To Do | Developer |  |  |  | Define base architecture
HU-02 | HU-02-T01 | Add PostgreSQL to Docker Compose | Phase 1 | Project Foundation | Infrastructure | High | To Do | Developer |  |  |  | Configure local infrastructure
HU-02 | HU-02-T02 | Add RabbitMQ to Docker Compose | Phase 1 | Project Foundation | Infrastructure | High | To Do | Developer |  |  |  | Configure local infrastructure
HU-02 | HU-02-T03 | Add MinIO to Docker Compose | Phase 1 | Project Foundation | Infrastructure | High | To Do | Developer |  |  |  | Configure local infrastructure
HU-02 | HU-02-T04 | Add Prometheus to Docker Compose | Phase 1 | Project Foundation | Infrastructure | High | To Do | Developer |  |  |  | Configure local infrastructure
HU-02 | HU-02-T05 | Add Grafana to Docker Compose | Phase 1 | Project Foundation | Infrastructure | High | To Do | Developer |  |  |  | Configure local infrastructure
HU-02 | HU-02-T06 | Create internal networks | Phase 1 | Project Foundation | Infrastructure | High | To Do | Developer |  |  |  | Configure local infrastructure
HU-02 | HU-02-T07 | Create persistent volumes | Phase 1 | Project Foundation | Infrastructure | High | To Do | Developer |  |  |  | Configure local infrastructure
HU-02 | HU-02-T08 | Test connections between services | Phase 1 | Project Foundation | Infrastructure | High | To Do | Developer |  |  |  | Configure local infrastructure
HU-03 | HU-03-T01 | Create Go service for API Gateway | Phase 1 | Project Foundation | API Gateway | High | To Do | Backend |  |  |  | Create API Gateway
HU-03 | HU-03-T02 | Configure HTTP router | Phase 1 | Project Foundation | API Gateway | High | To Do | Backend |  |  |  | Create API Gateway
HU-03 | HU-03-T03 | Create health check endpoint | Phase 1 | Project Foundation | API Gateway | High | To Do | Backend |  |  |  | Create API Gateway
HU-03 | HU-03-T04 | Configure CORS | Phase 1 | Project Foundation | API Gateway | High | To Do | Backend |  |  |  | Create API Gateway
HU-03 | HU-03-T05 | Configure environment variable loading | Phase 1 | Project Foundation | API Gateway | High | To Do | Backend |  |  |  | Create API Gateway
HU-03 | HU-03-T06 | Add logging middleware | Phase 1 | Project Foundation | API Gateway | High | To Do | Backend |  |  |  | Create API Gateway
HU-03 | HU-03-T07 | Add authentication middleware | Phase 1 | Project Foundation | API Gateway | High | To Do | Backend |  |  |  | Create API Gateway
HU-03 | HU-03-T08 | Document initial endpoints | Phase 1 | Project Foundation | API Gateway | High | To Do | Backend |  |  |  | Create API Gateway
HU-04 | HU-04-T01 | Create users table | Phase 2 | Security and Users | Auth | High | To Do | Backend/Frontend |  |  |  | Register user
HU-04 | HU-04-T02 | Create registration endpoint | Phase 2 | Security and Users | Auth | High | To Do | Backend/Frontend |  |  |  | Register user
HU-04 | HU-04-T03 | Validate name, email, and password | Phase 2 | Security and Users | Auth | High | To Do | Backend/Frontend |  |  |  | Register user
HU-04 | HU-04-T04 | Hash password | Phase 2 | Security and Users | Auth | High | To Do | Backend/Frontend |  |  |  | Register user
HU-04 | HU-04-T05 | Store user | Phase 2 | Security and Users | Auth | High | To Do | Backend/Frontend |  |  |  | Register user
HU-04 | HU-04-T06 | Return safe response | Phase 2 | Security and Users | Auth | High | To Do | Backend/Frontend |  |  |  | Register user
HU-04 | HU-04-T07 | Add basic tests | Phase 2 | Security and Users | Auth | High | To Do | Backend/Frontend |  |  |  | Register user
HU-04 | HU-04-T08 | Create registration screen | Phase 2 | Security and Users | Auth | High | To Do | Backend/Frontend |  |  |  | Register user
HU-05 | HU-05-T01 | Create login endpoint | Phase 2 | Security and Users | Auth | High | To Do | Backend/Frontend |  |  |  | Sign in
HU-05 | HU-05-T02 | Validate credentials | Phase 2 | Security and Users | Auth | High | To Do | Backend/Frontend |  |  |  | Sign in
HU-05 | HU-05-T03 | Generate JWT | Phase 2 | Security and Users | Auth | High | To Do | Backend/Frontend |  |  |  | Sign in
HU-05 | HU-05-T04 | Return token or secure cookie | Phase 2 | Security and Users | Auth | High | To Do | Backend/Frontend |  |  |  | Sign in
HU-05 | HU-05-T05 | Protect private routes | Phase 2 | Security and Users | Auth | High | To Do | Backend/Frontend |  |  |  | Sign in
HU-05 | HU-05-T06 | Create login screen | Phase 2 | Security and Users | Auth | High | To Do | Backend/Frontend |  |  |  | Sign in
HU-05 | HU-05-T07 | Store session in frontend | Phase 2 | Security and Users | Auth | High | To Do | Backend/Frontend |  |  |  | Sign in
HU-05 | HU-05-T08 | Handle authentication errors | Phase 2 | Security and Users | Auth | High | To Do | Backend/Frontend |  |  |  | Sign in
HU-06 | HU-06-T01 | Add role field to users | Phase 2 | Security and Users | Auth | High | To Do | Backend/Frontend |  |  |  | Manage roles
HU-06 | HU-06-T02 | Define allowed roles | Phase 2 | Security and Users | Auth | High | To Do | Backend/Frontend |  |  |  | Manage roles
HU-06 | HU-06-T03 | Create authorization middleware | Phase 2 | Security and Users | Auth | High | To Do | Backend/Frontend |  |  |  | Manage roles
HU-06 | HU-06-T04 | Protect endpoints by role | Phase 2 | Security and Users | Auth | High | To Do | Backend/Frontend |  |  |  | Manage roles
HU-06 | HU-06-T05 | Create endpoint to change role | Phase 2 | Security and Users | Auth | High | To Do | Backend/Frontend |  |  |  | Manage roles
HU-06 | HU-06-T06 | Create simple users screen | Phase 2 | Security and Users | Auth | High | To Do | Backend/Frontend |  |  |  | Manage roles
HU-06 | HU-06-T07 | Register changes in audit trail | Phase 2 | Security and Users | Auth | High | To Do | Backend/Frontend |  |  |  | Manage roles
HU-07 | HU-07-T01 | Create cases table | Phase 3 | Cases and Evidence | Cases | High | To Do | Backend/Frontend |  |  |  | Create case
HU-07 | HU-07-T02 | Create POST /cases endpoint | Phase 3 | Cases and Evidence | Cases | High | To Do | Backend/Frontend |  |  |  | Create case
HU-07 | HU-07-T03 | Validate title, description, and priority | Phase 3 | Cases and Evidence | Cases | High | To Do | Backend/Frontend |  |  |  | Create case
HU-07 | HU-07-T04 | Associate case to creator user | Phase 3 | Cases and Evidence | Cases | High | To Do | Backend/Frontend |  |  |  | Create case
HU-07 | HU-07-T05 | Store initial draft state | Phase 3 | Cases and Evidence | Cases | High | To Do | Backend/Frontend |  |  |  | Create case
HU-07 | HU-07-T06 | Create frontend form | Phase 3 | Cases and Evidence | Cases | High | To Do | Backend/Frontend |  |  |  | Create case
HU-07 | HU-07-T07 | Show confirmation | Phase 3 | Cases and Evidence | Cases | High | To Do | Backend/Frontend |  |  |  | Create case
HU-07 | HU-07-T08 | Register action in audit trail | Phase 3 | Cases and Evidence | Cases | High | To Do | Backend/Frontend |  |  |  | Create case
HU-08 | HU-08-T01 | Create GET /cases endpoint | Phase 3 | Cases and Evidence | Cases | Medium | To Do | Backend/Frontend |  |  |  | List and filter cases
HU-08 | HU-08-T02 | Add filters by status, priority, and date | Phase 3 | Cases and Evidence | Cases | Medium | To Do | Backend/Frontend |  |  |  | List and filter cases
HU-08 | HU-08-T03 | Add pagination | Phase 3 | Cases and Evidence | Cases | Medium | To Do | Backend/Frontend |  |  |  | List and filter cases
HU-08 | HU-08-T04 | Create list screen | Phase 3 | Cases and Evidence | Cases | Medium | To Do | Backend/Frontend |  |  |  | List and filter cases
HU-08 | HU-08-T05 | Show status badges | Phase 3 | Cases and Evidence | Cases | Medium | To Do | Backend/Frontend |  |  |  | List and filter cases
HU-08 | HU-08-T06 | Show visual priority | Phase 3 | Cases and Evidence | Cases | Medium | To Do | Backend/Frontend |  |  |  | List and filter cases
HU-08 | HU-08-T07 | Add title search | Phase 3 | Cases and Evidence | Cases | Medium | To Do | Backend/Frontend |  |  |  | List and filter cases
HU-08 | HU-08-T08 | Handle loading and errors | Phase 3 | Cases and Evidence | Cases | Medium | To Do | Backend/Frontend |  |  |  | List and filter cases
HU-09 | HU-09-T01 | Create GET /cases/{id} endpoint | Phase 3 | Cases and Evidence | Cases | High | To Do | Backend/Frontend |  |  |  | View case details
HU-09 | HU-09-T02 | Fetch associated evidence | Phase 3 | Cases and Evidence | Cases | High | To Do | Backend/Frontend |  |  |  | View case details
HU-09 | HU-09-T03 | Fetch associated tasks | Phase 3 | Cases and Evidence | Cases | High | To Do | Backend/Frontend |  |  |  | View case details
HU-09 | HU-09-T04 | Fetch associated findings | Phase 3 | Cases and Evidence | Cases | High | To Do | Backend/Frontend |  |  |  | View case details
HU-09 | HU-09-T05 | Fetch report if available | Phase 3 | Cases and Evidence | Cases | High | To Do | Backend/Frontend |  |  |  | View case details
HU-09 | HU-09-T06 | Create detail screen | Phase 3 | Cases and Evidence | Cases | High | To Do | Backend/Frontend |  |  |  | View case details
HU-09 | HU-09-T07 | Create information sections | Phase 3 | Cases and Evidence | Cases | High | To Do | Backend/Frontend |  |  |  | View case details
HU-09 | HU-09-T08 | Add main actions | Phase 3 | Cases and Evidence | Cases | High | To Do | Backend/Frontend |  |  |  | View case details
HU-10 | HU-10-T01 | Create PATCH /cases/{id} endpoint | Phase 3 | Cases and Evidence | Cases | Medium | To Do | Backend/Frontend |  |  |  | Update case
HU-10 | HU-10-T02 | Validate permissions | Phase 3 | Cases and Evidence | Cases | Medium | To Do | Backend/Frontend |  |  |  | Update case
HU-10 | HU-10-T03 | Validate editable fields | Phase 3 | Cases and Evidence | Cases | Medium | To Do | Backend/Frontend |  |  |  | Update case
HU-10 | HU-10-T04 | Update data | Phase 3 | Cases and Evidence | Cases | Medium | To Do | Backend/Frontend |  |  |  | Update case
HU-10 | HU-10-T05 | Register audit event | Phase 3 | Cases and Evidence | Cases | Medium | To Do | Backend/Frontend |  |  |  | Update case
HU-10 | HU-10-T06 | Update detail screen | Phase 3 | Cases and Evidence | Cases | Medium | To Do | Backend/Frontend |  |  |  | Update case
HU-10 | HU-10-T07 | Handle non-editable states | Phase 3 | Cases and Evidence | Cases | Medium | To Do | Backend/Frontend |  |  |  | Update case
HU-11 | HU-11-T01 | Create evidences table | Phase 3 | Cases and Evidence | Evidence | High | To Do | Backend/Frontend |  |  |  | Upload evidence
HU-11 | HU-11-T02 | Create multipart POST /cases/{id}/evidences endpoint | Phase 3 | Cases and Evidence | Evidence | High | To Do | Backend/Frontend |  |  |  | Upload evidence
HU-11 | HU-11-T03 | Validate file | Phase 3 | Cases and Evidence | Evidence | High | To Do | Backend/Frontend |  |  |  | Upload evidence
HU-11 | HU-11-T04 | Calculate SHA-256 hash | Phase 3 | Cases and Evidence | Evidence | High | To Do | Backend/Frontend |  |  |  | Upload evidence
HU-11 | HU-11-T05 | Store file in MinIO | Phase 3 | Cases and Evidence | Evidence | High | To Do | Backend/Frontend |  |  |  | Upload evidence
HU-11 | HU-11-T06 | Store metadata in PostgreSQL | Phase 3 | Cases and Evidence | Evidence | High | To Do | Backend/Frontend |  |  |  | Upload evidence
HU-11 | HU-11-T07 | Show evidence in case | Phase 3 | Cases and Evidence | Evidence | High | To Do | Backend/Frontend |  |  |  | Upload evidence
HU-11 | HU-11-T08 | Register audit event | Phase 3 | Cases and Evidence | Evidence | High | To Do | Backend/Frontend |  |  |  | Upload evidence
HU-12 | HU-12-T01 | Define allowed extensions | Phase 3 | Cases and Evidence | Evidence | High | To Do | Backend |  |  |  | Validate evidence
HU-12 | HU-12-T02 | Define maximum size | Phase 3 | Cases and Evidence | Evidence | High | To Do | Backend |  |  |  | Validate evidence
HU-12 | HU-12-T03 | Validate MIME type | Phase 3 | Cases and Evidence | Evidence | High | To Do | Backend |  |  |  | Validate evidence
HU-12 | HU-12-T04 | Validate empty file | Phase 3 | Cases and Evidence | Evidence | High | To Do | Backend |  |  |  | Validate evidence
HU-12 | HU-12-T05 | Avoid duplicates by hash | Phase 3 | Cases and Evidence | Evidence | High | To Do | Backend |  |  |  | Validate evidence
HU-12 | HU-12-T06 | Return clear errors | Phase 3 | Cases and Evidence | Evidence | High | To Do | Backend |  |  |  | Validate evidence
HU-12 | HU-12-T07 | Add validation tests | Phase 3 | Cases and Evidence | Evidence | High | To Do | Backend |  |  |  | Validate evidence
HU-13 | HU-13-T01 | Create MIME/extension classification function | Phase 3 | Cases and Evidence | Evidence | High | To Do | Backend |  |  |  | Classify evidence
HU-13 | HU-13-T02 | Define types: text, image, audio, document, archive | Phase 3 | Cases and Evidence | Evidence | High | To Do | Backend |  |  |  | Classify evidence
HU-13 | HU-13-T03 | Update state to classified | Phase 3 | Cases and Evidence | Evidence | High | To Do | Backend |  |  |  | Classify evidence
HU-13 | HU-13-T04 | Store type in database | Phase 3 | Cases and Evidence | Evidence | High | To Do | Backend |  |  |  | Classify evidence
HU-13 | HU-13-T05 | Notify Task Orchestrator | Phase 3 | Cases and Evidence | Evidence | High | To Do | Backend |  |  |  | Classify evidence
HU-13 | HU-13-T06 | Create tests with sample files | Phase 3 | Cases and Evidence | Evidence | High | To Do | Backend |  |  |  | Classify evidence
HU-14 | HU-14-T01 | Create tasks table | Phase 4 | Distributed Orchestration | Tasks | High | To Do | Backend |  |  |  | Create tasks automatically
HU-14 | HU-14-T02 | Create Task Orchestrator service | Phase 4 | Distributed Orchestration | Tasks | High | To Do | Backend |  |  |  | Create tasks automatically
HU-14 | HU-14-T03 | Define task creation rules | Phase 4 | Distributed Orchestration | Tasks | High | To Do | Backend |  |  |  | Create tasks automatically
HU-14 | HU-14-T04 | Create tasks by evidence type | Phase 4 | Distributed Orchestration | Tasks | High | To Do | Backend |  |  |  | Create tasks automatically
HU-14 | HU-14-T05 | Assign priority inherited from case | Phase 4 | Distributed Orchestration | Tasks | High | To Do | Backend |  |  |  | Create tasks automatically
HU-14 | HU-14-T06 | Store tasks in PostgreSQL | Phase 4 | Distributed Orchestration | Tasks | High | To Do | Backend |  |  |  | Create tasks automatically
HU-14 | HU-14-T07 | Update evidence state | Phase 4 | Distributed Orchestration | Tasks | High | To Do | Backend |  |  |  | Create tasks automatically
HU-14 | HU-14-T08 | Prepare RabbitMQ event | Phase 4 | Distributed Orchestration | Tasks | High | To Do | Backend |  |  |  | Create tasks automatically
HU-15 | HU-15-T01 | Configure RabbitMQ connection | Phase 4 | Distributed Orchestration | Messaging | High | To Do | Backend |  |  |  | Queue tasks in RabbitMQ
HU-15 | HU-15-T02 | Create exchanges | Phase 4 | Distributed Orchestration | Messaging | High | To Do | Backend |  |  |  | Queue tasks in RabbitMQ
HU-15 | HU-15-T03 | Create queues by task type | Phase 4 | Distributed Orchestration | Messaging | High | To Do | Backend |  |  |  | Queue tasks in RabbitMQ
HU-15 | HU-15-T04 | Create priority queue | Phase 4 | Distributed Orchestration | Messaging | High | To Do | Backend |  |  |  | Queue tasks in RabbitMQ
HU-15 | HU-15-T05 | Publish message with task_id | Phase 4 | Distributed Orchestration | Messaging | High | To Do | Backend |  |  |  | Queue tasks in RabbitMQ
HU-15 | HU-15-T06 | Confirm publication | Phase 4 | Distributed Orchestration | Messaging | High | To Do | Backend |  |  |  | Queue tasks in RabbitMQ
HU-15 | HU-15-T07 | Update state to queued | Phase 4 | Distributed Orchestration | Messaging | High | To Do | Backend |  |  |  | Queue tasks in RabbitMQ
HU-15 | HU-15-T08 | Handle connection errors | Phase 4 | Distributed Orchestration | Messaging | High | To Do | Backend |  |  |  | Queue tasks in RabbitMQ
HU-16 | HU-16-T01 | Create text-worker in Python | Phase 5 | Workers | Text Worker | High | To Do | Worker |  |  |  | Process text
HU-16 | HU-16-T02 | Connect worker to RabbitMQ | Phase 5 | Workers | Text Worker | High | To Do | Worker |  |  |  | Process text
HU-16 | HU-16-T03 | Consume tasks from text queue | Phase 5 | Workers | Text Worker | High | To Do | Worker |  |  |  | Process text
HU-16 | HU-16-T04 | Read file from MinIO | Phase 5 | Workers | Text Worker | High | To Do | Worker |  |  |  | Process text
HU-16 | HU-16-T05 | Normalize text | Phase 5 | Workers | Text Worker | High | To Do | Worker |  |  |  | Process text
HU-16 | HU-16-T06 | Detect keywords | Phase 5 | Workers | Text Worker | High | To Do | Worker |  |  |  | Process text
HU-16 | HU-16-T07 | Classify categories | Phase 5 | Workers | Text Worker | High | To Do | Worker |  |  |  | Process text
HU-16 | HU-16-T08 | Calculate severity | Phase 5 | Workers | Text Worker | High | To Do | Worker |  |  |  | Process text
HU-16 | HU-16-T09 | Store findings | Phase 5 | Workers | Text Worker | High | To Do | Worker |  |  |  | Process text
HU-16 | HU-16-T10 | Mark task as completed | Phase 5 | Workers | Text Worker | High | To Do | Worker |  |  |  | Process text
HU-17 | HU-17-T01 | Create document-worker | Phase 5 | Workers | Document Worker | High | To Do | Worker |  |  |  | Process PDF documents
HU-17 | HU-17-T02 | Consume tasks from document queue | Phase 5 | Workers | Document Worker | High | To Do | Worker |  |  |  | Process PDF documents
HU-17 | HU-17-T03 | Download PDF from MinIO | Phase 5 | Workers | Document Worker | High | To Do | Worker |  |  |  | Process PDF documents
HU-17 | HU-17-T04 | Extract text | Phase 5 | Workers | Document Worker | High | To Do | Worker |  |  |  | Process PDF documents
HU-17 | HU-17-T05 | Store extracted text as processed artifact | Phase 5 | Workers | Document Worker | High | To Do | Worker |  |  |  | Process PDF documents
HU-17 | HU-17-T06 | Create secondary text analysis task | Phase 5 | Workers | Document Worker | High | To Do | Worker |  |  |  | Process PDF documents
HU-17 | HU-17-T07 | Handle PDFs without text | Phase 5 | Workers | Document Worker | High | To Do | Worker |  |  |  | Process PDF documents
HU-17 | HU-17-T08 | Register errors if document cannot be processed | Phase 5 | Workers | Document Worker | High | To Do | Worker |  |  |  | Process PDF documents
HU-18 | HU-18-T01 | Create image-worker | Phase 5 | Workers | Image Worker | Medium | To Do | Worker |  |  |  | Process images
HU-18 | HU-18-T02 | Consume tasks from image queue | Phase 5 | Workers | Image Worker | Medium | To Do | Worker |  |  |  | Process images
HU-18 | HU-18-T03 | Download image from MinIO | Phase 5 | Workers | Image Worker | Medium | To Do | Worker |  |  |  | Process images
HU-18 | HU-18-T04 | Run basic analysis with OpenCV or pretrained model | Phase 5 | Workers | Image Worker | Medium | To Do | Worker |  |  |  | Process images
HU-18 | HU-18-T05 | Generate detected labels | Phase 5 | Workers | Image Worker | Medium | To Do | Worker |  |  |  | Process images
HU-18 | HU-18-T06 | Calculate severity for risk matches | Phase 5 | Workers | Image Worker | Medium | To Do | Worker |  |  |  | Process images
HU-18 | HU-18-T07 | Store findings | Phase 5 | Workers | Image Worker | Medium | To Do | Worker |  |  |  | Process images
HU-18 | HU-18-T08 | Mark task as completed | Phase 5 | Workers | Image Worker | Medium | To Do | Worker |  |  |  | Process images
HU-19 | HU-19-T01 | Create audio-worker | Phase 5 | Workers | Audio Worker | Medium | To Do | Worker |  |  |  | Process audio
HU-19 | HU-19-T02 | Consume tasks from audio queue | Phase 5 | Workers | Audio Worker | Medium | To Do | Worker |  |  |  | Process audio
HU-19 | HU-19-T03 | Download audio from MinIO | Phase 5 | Workers | Audio Worker | Medium | To Do | Worker |  |  |  | Process audio
HU-19 | HU-19-T04 | Transcribe with Whisper or Vosk | Phase 5 | Workers | Audio Worker | Medium | To Do | Worker |  |  |  | Process audio
HU-19 | HU-19-T05 | Store transcription | Phase 5 | Workers | Audio Worker | Medium | To Do | Worker |  |  |  | Process audio
HU-19 | HU-19-T06 | Create secondary text analysis task | Phase 5 | Workers | Audio Worker | Medium | To Do | Worker |  |  |  | Process audio
HU-19 | HU-19-T07 | Handle invalid audio | Phase 5 | Workers | Audio Worker | Medium | To Do | Worker |  |  |  | Process audio
HU-19 | HU-19-T08 | Store duration and processing-time metrics | Phase 5 | Workers | Audio Worker | Medium | To Do | Worker |  |  |  | Process audio
HU-20 | HU-20-T01 | Create findings table | Phase 5 | Workers | Findings | High | To Do | Backend/Worker |  |  |  | Register findings
HU-20 | HU-20-T02 | Define categories | Phase 5 | Workers | Findings | High | To Do | Backend/Worker |  |  |  | Register findings
HU-20 | HU-20-T03 | Define severities | Phase 5 | Workers | Findings | High | To Do | Backend/Worker |  |  |  | Register findings
HU-20 | HU-20-T04 | Create internal endpoint to store findings | Phase 5 | Workers | Findings | High | To Do | Backend/Worker |  |  |  | Register findings
HU-20 | HU-20-T05 | Associate finding with case_id, evidence_id, and task_id | Phase 5 | Workers | Findings | High | To Do | Backend/Worker |  |  |  | Register findings
HU-20 | HU-20-T06 | Store evidence excerpt | Phase 5 | Workers | Findings | High | To Do | Backend/Worker |  |  |  | Register findings
HU-20 | HU-20-T07 | Store confidence and metadata | Phase 5 | Workers | Findings | High | To Do | Backend/Worker |  |  |  | Register findings
HU-20 | HU-20-T08 | Show findings in frontend | Phase 5 | Workers | Findings | High | To Do | Backend/Worker |  |  |  | Register findings
HU-21 | HU-21-T01 | Define risk formula | Phase 5 | Workers | Risk | Medium | To Do | Backend |  |  |  | Calculate case risk
HU-21 | HU-21-T02 | Assign weights by severity | Phase 5 | Workers | Risk | Medium | To Do | Backend |  |  |  | Calculate case risk
HU-21 | HU-21-T03 | Calculate risk by evidence | Phase 5 | Workers | Risk | Medium | To Do | Backend |  |  |  | Calculate case risk
HU-21 | HU-21-T04 | Calculate overall case risk | Phase 5 | Workers | Risk | Medium | To Do | Backend |  |  |  | Calculate case risk
HU-21 | HU-21-T05 | Update case when findings change | Phase 5 | Workers | Risk | Medium | To Do | Backend |  |  |  | Calculate case risk
HU-21 | HU-21-T06 | Show score in dashboard | Phase 5 | Workers | Risk | Medium | To Do | Backend |  |  |  | Calculate case risk
HU-21 | HU-21-T07 | Document formula | Phase 5 | Workers | Risk | Medium | To Do | Backend |  |  |  | Calculate case risk
HU-22 | HU-22-T01 | Create report-service | Phase 6 | Results | Reports | High | To Do | Backend |  |  |  | Generate report
HU-22 | HU-22-T02 | Create reports table | Phase 6 | Results | Reports | High | To Do | Backend |  |  |  | Generate report
HU-22 | HU-22-T03 | Fetch case data | Phase 6 | Results | Reports | High | To Do | Backend |  |  |  | Generate report
HU-22 | HU-22-T04 | Fetch evidence | Phase 6 | Results | Reports | High | To Do | Backend |  |  |  | Generate report
HU-22 | HU-22-T05 | Fetch findings | Phase 6 | Results | Reports | High | To Do | Backend |  |  |  | Generate report
HU-22 | HU-22-T06 | Fetch tasks and workers | Phase 6 | Results | Reports | High | To Do | Backend |  |  |  | Generate report
HU-22 | HU-22-T07 | Generate summary | Phase 6 | Results | Reports | High | To Do | Backend |  |  |  | Generate report
HU-22 | HU-22-T08 | Create PDF | Phase 6 | Results | Reports | High | To Do | Backend |  |  |  | Generate report
HU-22 | HU-22-T09 | Store PDF in MinIO | Phase 6 | Results | Reports | High | To Do | Backend |  |  |  | Generate report
HU-22 | HU-22-T10 | Register report in PostgreSQL | Phase 6 | Results | Reports | High | To Do | Backend |  |  |  | Generate report
HU-23 | HU-23-T01 | Create GET /cases/{id}/report endpoint | Phase 6 | Results | Reports | Medium | To Do | Backend/Frontend |  |  |  | Download and view report
HU-23 | HU-23-T02 | Fetch report metadata | Phase 6 | Results | Reports | Medium | To Do | Backend/Frontend |  |  |  | Download and view report
HU-23 | HU-23-T03 | Generate temporary MinIO URL | Phase 6 | Results | Reports | Medium | To Do | Backend/Frontend |  |  |  | Download and view report
HU-23 | HU-23-T04 | Create frontend button | Phase 6 | Results | Reports | Medium | To Do | Backend/Frontend |  |  |  | Download and view report
HU-23 | HU-23-T05 | Show report summary | Phase 6 | Results | Reports | Medium | To Do | Backend/Frontend |  |  |  | Download and view report
HU-23 | HU-23-T06 | Handle report not generated | Phase 6 | Results | Reports | Medium | To Do | Backend/Frontend |  |  |  | Download and view report
HU-23 | HU-23-T07 | Register download in audit trail | Phase 6 | Results | Reports | Medium | To Do | Backend/Frontend |  |  |  | Download and view report
HU-24 | HU-24-T01 | Create application metrics endpoint | Phase 7 | Monitoring and Presentation | Dashboard | High | To Do | Backend/Frontend |  |  |  | General dashboard
HU-24 | HU-24-T02 | Count cases by state | Phase 7 | Monitoring and Presentation | Dashboard | High | To Do | Backend/Frontend |  |  |  | General dashboard
HU-24 | HU-24-T03 | Count tasks by state | Phase 7 | Monitoring and Presentation | Dashboard | High | To Do | Backend/Frontend |  |  |  | General dashboard
HU-24 | HU-24-T04 | Count processed evidence | Phase 7 | Monitoring and Presentation | Dashboard | High | To Do | Backend/Frontend |  |  |  | General dashboard
HU-24 | HU-24-T05 | Show active workers | Phase 7 | Monitoring and Presentation | Dashboard | High | To Do | Backend/Frontend |  |  |  | General dashboard
HU-24 | HU-24-T06 | Show failed tasks | Phase 7 | Monitoring and Presentation | Dashboard | High | To Do | Backend/Frontend |  |  |  | General dashboard
HU-24 | HU-24-T07 | Create statistic cards | Phase 7 | Monitoring and Presentation | Dashboard | High | To Do | Backend/Frontend |  |  |  | General dashboard
HU-24 | HU-24-T08 | Create simple charts | Phase 7 | Monitoring and Presentation | Dashboard | High | To Do | Backend/Frontend |  |  |  | General dashboard
HU-25 | HU-25-T01 | Choose SSE or WebSockets | Phase 7 | Monitoring and Presentation | Realtime | Medium | To Do | Backend/Frontend |  |  |  | Real-time updates
HU-25 | HU-25-T02 | Create event channel | Phase 7 | Monitoring and Presentation | Realtime | Medium | To Do | Backend/Frontend |  |  |  | Real-time updates
HU-25 | HU-25-T03 | Emit task status changed events | Phase 7 | Monitoring and Presentation | Realtime | Medium | To Do | Backend/Frontend |  |  |  | Real-time updates
HU-25 | HU-25-T04 | Emit case status changed events | Phase 7 | Monitoring and Presentation | Realtime | Medium | To Do | Backend/Frontend |  |  |  | Real-time updates
HU-25 | HU-25-T05 | Consume events in frontend | Phase 7 | Monitoring and Presentation | Realtime | Medium | To Do | Backend/Frontend |  |  |  | Real-time updates
HU-25 | HU-25-T06 | Update dashboard without reload | Phase 7 | Monitoring and Presentation | Realtime | Medium | To Do | Backend/Frontend |  |  |  | Real-time updates
HU-25 | HU-25-T07 | Handle reconnection | Phase 7 | Monitoring and Presentation | Realtime | Medium | To Do | Backend/Frontend |  |  |  | Real-time updates
HU-25 | HU-25-T08 | Document events | Phase 7 | Monitoring and Presentation | Realtime | Medium | To Do | Backend/Frontend |  |  |  | Real-time updates
HU-26 | HU-26-T01 | Create notifications table | Phase 6 | Results | Notifications | Medium | To Do | Backend/Frontend |  |  |  | Internal alerts
HU-26 | HU-26-T02 | Create notification-service | Phase 6 | Results | Notifications | Medium | To Do | Backend/Frontend |  |  |  | Internal alerts
HU-26 | HU-26-T03 | Define alert rules | Phase 6 | Results | Notifications | Medium | To Do | Backend/Frontend |  |  |  | Internal alerts
HU-26 | HU-26-T04 | Emit alert if severity is high or critical | Phase 6 | Results | Notifications | Medium | To Do | Backend/Frontend |  |  |  | Internal alerts
HU-26 | HU-26-T05 | Show notifications in frontend | Phase 6 | Results | Notifications | Medium | To Do | Backend/Frontend |  |  |  | Internal alerts
HU-26 | HU-26-T06 | Mark notifications as read | Phase 6 | Results | Notifications | Medium | To Do | Backend/Frontend |  |  |  | Internal alerts
HU-26 | HU-26-T07 | Register event in audit trail | Phase 6 | Results | Notifications | Medium | To Do | Backend/Frontend |  |  |  | Internal alerts
HU-27 | HU-27-T01 | Add retry_count to tasks | Phase 4 | Distributed Orchestration | Messaging | High | To Do | Backend |  |  |  | Retries and dead-letter queue
HU-27 | HU-27-T02 | Define max_retries | Phase 4 | Distributed Orchestration | Messaging | High | To Do | Backend |  |  |  | Retries and dead-letter queue
HU-27 | HU-27-T03 | Configure retries in RabbitMQ | Phase 4 | Distributed Orchestration | Messaging | High | To Do | Backend |  |  |  | Retries and dead-letter queue
HU-27 | HU-27-T04 | Update state to retrying | Phase 4 | Distributed Orchestration | Messaging | High | To Do | Backend |  |  |  | Retries and dead-letter queue
HU-27 | HU-27-T05 | Move to dead-letter if max is exceeded | Phase 4 | Distributed Orchestration | Messaging | High | To Do | Backend |  |  |  | Retries and dead-letter queue
HU-27 | HU-27-T06 | Register error_message | Phase 4 | Distributed Orchestration | Messaging | High | To Do | Backend |  |  |  | Retries and dead-letter queue
HU-27 | HU-27-T07 | Show failed tasks in dashboard | Phase 4 | Distributed Orchestration | Messaging | High | To Do | Backend |  |  |  | Retries and dead-letter queue
HU-27 | HU-27-T08 | Allow manual retry | Phase 4 | Distributed Orchestration | Messaging | High | To Do | Backend |  |  |  | Retries and dead-letter queue
HU-28 | HU-28-T01 | Create cancellation endpoint | Phase 4 | Distributed Orchestration | Tasks | Medium | To Do | Backend/Frontend |  |  |  | Cancel task or case
HU-28 | HU-28-T02 | Validate current state | Phase 4 | Distributed Orchestration | Tasks | Medium | To Do | Backend/Frontend |  |  |  | Cancel task or case
HU-28 | HU-28-T03 | Mark tasks as cancelled | Phase 4 | Distributed Orchestration | Tasks | Medium | To Do | Backend/Frontend |  |  |  | Cancel task or case
HU-28 | HU-28-T04 | Avoid consuming cancelled tasks | Phase 4 | Distributed Orchestration | Tasks | Medium | To Do | Backend/Frontend |  |  |  | Cancel task or case
HU-28 | HU-28-T05 | Update case | Phase 4 | Distributed Orchestration | Tasks | Medium | To Do | Backend/Frontend |  |  |  | Cancel task or case
HU-28 | HU-28-T06 | Notify dashboard | Phase 4 | Distributed Orchestration | Tasks | Medium | To Do | Backend/Frontend |  |  |  | Cancel task or case
HU-28 | HU-28-T07 | Register audit event | Phase 4 | Distributed Orchestration | Tasks | Medium | To Do | Backend/Frontend |  |  |  | Cancel task or case
HU-29 | HU-29-T01 | Create audit_logs table | Phase 7 | Monitoring and Presentation | Audit | Medium | To Do | Backend/Frontend |  |  |  | Audit trail
HU-29 | HU-29-T02 | Create audit middleware | Phase 7 | Monitoring and Presentation | Audit | Medium | To Do | Backend/Frontend |  |  |  | Audit trail
HU-29 | HU-29-T03 | Register case creation | Phase 7 | Monitoring and Presentation | Audit | Medium | To Do | Backend/Frontend |  |  |  | Audit trail
HU-29 | HU-29-T04 | Register evidence upload | Phase 7 | Monitoring and Presentation | Audit | Medium | To Do | Backend/Frontend |  |  |  | Audit trail
HU-29 | HU-29-T05 | Register state changes | Phase 7 | Monitoring and Presentation | Audit | Medium | To Do | Backend/Frontend |  |  |  | Audit trail
HU-29 | HU-29-T06 | Register report downloads | Phase 7 | Monitoring and Presentation | Audit | Medium | To Do | Backend/Frontend |  |  |  | Audit trail
HU-29 | HU-29-T07 | Create query endpoint | Phase 7 | Monitoring and Presentation | Audit | Medium | To Do | Backend/Frontend |  |  |  | Audit trail
HU-29 | HU-29-T08 | Create audit screen | Phase 7 | Monitoring and Presentation | Audit | Medium | To Do | Backend/Frontend |  |  |  | Audit trail
HU-30 | HU-30-T01 | Add /metrics endpoint | Phase 7 | Monitoring and Presentation | Observability | High | To Do | DevOps |  |  |  | Metrics and observability
HU-30 | HU-30-T02 | Measure processed tasks | Phase 7 | Monitoring and Presentation | Observability | High | To Do | DevOps |  |  |  | Metrics and observability
HU-30 | HU-30-T03 | Measure average worker time | Phase 7 | Monitoring and Presentation | Observability | High | To Do | DevOps |  |  |  | Metrics and observability
HU-30 | HU-30-T04 | Measure errors by service | Phase 7 | Monitoring and Presentation | Observability | High | To Do | DevOps |  |  |  | Metrics and observability
HU-30 | HU-30-T05 | Configure Prometheus | Phase 7 | Monitoring and Presentation | Observability | High | To Do | DevOps |  |  |  | Metrics and observability
HU-30 | HU-30-T06 | Configure Grafana | Phase 7 | Monitoring and Presentation | Observability | High | To Do | DevOps |  |  |  | Metrics and observability
HU-30 | HU-30-T07 | Create metrics dashboard | Phase 7 | Monitoring and Presentation | Observability | High | To Do | DevOps |  |  |  | Metrics and observability
HU-30 | HU-30-T08 | Document results | Phase 7 | Monitoring and Presentation | Observability | High | To Do | DevOps |  |  |  | Metrics and observability
HU-31 | HU-31-T01 | Create test dataset | Phase 7 | Monitoring and Presentation | Load Testing | Medium | To Do | QA/DevOps |  |  |  | Load testing
HU-31 | HU-31-T02 | Create script to upload multiple evidence files | Phase 7 | Monitoring and Presentation | Load Testing | Medium | To Do | QA/DevOps |  |  |  | Load testing
HU-31 | HU-31-T03 | Measure time with 1 worker | Phase 7 | Monitoring and Presentation | Load Testing | Medium | To Do | QA/DevOps |  |  |  | Load testing
HU-31 | HU-31-T04 | Measure time with 3 workers | Phase 7 | Monitoring and Presentation | Load Testing | Medium | To Do | QA/DevOps |  |  |  | Load testing
HU-31 | HU-31-T05 | Measure time with 5 workers | Phase 7 | Monitoring and Presentation | Load Testing | Medium | To Do | QA/DevOps |  |  |  | Load testing
HU-31 | HU-31-T06 | Compare results | Phase 7 | Monitoring and Presentation | Load Testing | Medium | To Do | QA/DevOps |  |  |  | Load testing
HU-31 | HU-31-T07 | Create performance table | Phase 7 | Monitoring and Presentation | Load Testing | Medium | To Do | QA/DevOps |  |  |  | Load testing
HU-31 | HU-31-T08 | Add results to final report | Phase 7 | Monitoring and Presentation | Load Testing | Medium | To Do | QA/DevOps |  |  |  | Load testing
HU-32 | HU-32-T01 | Create main README | Phase 7 | Monitoring and Presentation | Docs | Medium | To Do | Documentation |  |  |  | Project documentation
HU-32 | HU-32-T02 | Document architecture | Phase 7 | Monitoring and Presentation | Docs | Medium | To Do | Documentation |  |  |  | Project documentation
HU-32 | HU-32-T03 | Document environment variables | Phase 7 | Monitoring and Presentation | Docs | Medium | To Do | Documentation |  |  |  | Project documentation
HU-32 | HU-32-T04 | Document endpoints | Phase 7 | Monitoring and Presentation | Docs | Medium | To Do | Documentation |  |  |  | Project documentation
HU-32 | HU-32-T05 | Document workers | Phase 7 | Monitoring and Presentation | Docs | Medium | To Do | Documentation |  |  |  | Project documentation
HU-32 | HU-32-T06 | Document Docker Compose | Phase 7 | Monitoring and Presentation | Docs | Medium | To Do | Documentation |  |  |  | Project documentation
HU-32 | HU-32-T07 | Add diagrams | Phase 7 | Monitoring and Presentation | Docs | Medium | To Do | Documentation |  |  |  | Project documentation
HU-32 | HU-32-T08 | Add testing guide | Phase 7 | Monitoring and Presentation | Docs | Medium | To Do | Documentation |  |  |  | Project documentation
HU-32 | HU-32-T09 | Add license | Phase 7 | Monitoring and Presentation | Docs | Medium | To Do | Documentation |  |  |  | Project documentation
HU-32 | HU-32-T10 | Add roadmap | Phase 7 | Monitoring and Presentation | Docs | Medium | To Do | Documentation |  |  |  | Project documentation

## Roadmap
Phase | Name | User Stories
Phase 1 | Project Foundation | HU-00, HU-01, HU-02, HU-03
Phase 2 | Security and Users | HU-04, HU-05, HU-06
Phase 3 | Cases and Evidence | HU-07, HU-08, HU-09, HU-10, HU-11, HU-12, HU-13
Phase 4 | Distributed Orchestration | HU-14, HU-15, HU-27, HU-28
Phase 5 | Workers | HU-16, HU-17, HU-18, HU-19, HU-20, HU-21
Phase 6 | Results | HU-22, HU-23, HU-26
Phase 7 | Monitoring and Presentation | HU-24, HU-25, HU-29, HU-30, HU-31, HU-32

## Lists
To Do | Critical | Must Have | Phase 1
In Progress | High | Should Have | Phase 2
Blocked | Medium | Could Have | Phase 3
In Review | Low | Won't Have | Phase 4
Done |  |  | Phase 5
Phase 6
Phase 7